## DMA Website Edits Tracker
# | Section | Category | Issue Description | Recommended Correction | Status | What Was Done (for completed items) | Commit Reference
HEADER SECTION
1 | Header | Appearance | David Mary Logo: Less projected visibility | Change to WHITE background to blend with logo | DONE | Logo updated with white/rounded background styling in header component | ec6717a, 3134420
2 | Header | Top Navigation | Navigation menu not fixed on scroll | Freeze it regardless of page or scrolling | DONE | Header set to fixed position with "fixed top-0 left-0 right-0 z-50" CSS classes | 3134420
3 | Header | Search Bar | Search bar requested initially, then removed | Remove Search Bar | DONE | Search bar removed from header component | aa1eed8
HERO BANNER SECTION
4 | Hero Banner | Redundant | "Explore Programs" button redundant to Our Programs in nav | Remove "Explore Programs" button | DONE | Button removed from hero banner template | 64e3e2f
5 | Hero Banner | Content | Tagline says "A premier preschool offering Cambridge curriculum..." | Replace with "Moulding a confident generation, in the Culture of Honor!" | DONE | Hero subheading updated to new tagline text | 64e3e2f, a8c9d7a
6 | Hero Banner | Appearance | 3 tiles (Blended Curriculum, Expert Teachers, Fun Learning) in hero | Remove tiles from hero banner; move to About Us as Key Highlights | DONE | Removed all 3 feature tiles from hero banner; replaced with centered Enquiry Form button/banner
7 | Hero Banner | Function | Replace "Blended Curriculum" tile with Enquiry Form link | Link to Google Form: https://forms.gle/doqF1H7TbdVW2uhk9 | DONE | Added centered Enquiry Form button below hero linking to https://forms.gle/doqF1H7TbdVW2uhk9
8 | Hero Banner | Function | "Apply for Admission/Enroll Now" button functionality | Form submission should notify the school immediately | DONE | Button linked to JotForm which handles submissions and notifications | a8c9d7a
9 | Hero Banner | Appearance | Academic Year admissions projection needed | Admissions info to be prominently displayed | DONE | Admission banner/CTA added prominently in hero section | a8c9d7a
ABOUT US SECTION
10 | About Us | Redundant | "Explore our programs" button exists | Remove button | DONE | Button removed from About Us section template | 64e3e2f
11 | About Us | Redundant | "Our Values" tile exists | Remove "Our Values" tile | DONE | Our Values section removed from About Us component | 64e3e2f
12 | About Us | Redundant | "Why Parents Choose Us" section redundant with "Why Choose Us" | Remove "Why Parents Choose Us" | DONE | Section removed; consolidated into "What We Offer" section | 64e3e2f
13 | About Us | Function | "Learn why Parents choose us" hyperlink not working | Link should redirect to testimonials page with parents photo | DONE | Section removed entirely, eliminating the broken link | 64e3e2f
14 | About Us | Content | Our Mission text needs updating | Update to approved text about safe, nurturing environment | DONE | Mission text updated with full approved content about wisdom, strength, and character | 64e3e2f
15 | About Us | Content | Our Vision text needs updating to DMA-approved version | Update to final version with David and Mary example: "We have examples of David and Mary who in humility and obedience were prepared for a greater purpose..." | DONE | Vision updated to DMA-approved version with Courage, Character, and Creativity and David & Mary example
16 | About Us | Deleted | "Our Approach" section should be removed | Delete "Our Approach" section entirely | DONE | Entire Our Approach section deleted (heading, bullet list, learn why parents choose us link, learning.png image)
17 | About Us | Images | Current photo needs replacement | Include different/new photos | PENDING
OUR PROGRAMS SECTION
18 | Our Programs | Content | Subheading exists under "Our Program" | Remove subheading | DONE | Subheading removed from programs section | 64e3e2f
19 | Our Programs | Function | "View Schedule" button not functioning | Fix and show daily schedule (9:00 AM - 12:30 PM with activities list) | DONE | Schedule modal implemented with Circle Time, Free Play, Story Time, Snack Break, Crafts, Language/Numeracy, Sports | a8c9d7a
20 | Our Programs | Button | "Apply Admission" button in programs | Remove button | DONE | Apply Admission button removed from program cards | 64e3e2f
21 | Our Programs | Content | Common Features says "Cambridge" | Replace "Cambridge" with "Blended" | DONE | All references changed from Cambridge to Blended Curriculum | 64e3e2f
22 | Our Programs | Content | "Low student to staff ratio" in common features | Remove it | DONE | Removed from common features list | 64e3e2f
23 | Our Programs | Content | Missing "Emotional & Social Development" and "Safety & Hygiene" | Add both to common features | DONE | Both items added to the common features section | 64e3e2f
24 | Our Programs | Content | Schedule content needed for Pre-K, Junior K, Senior K | Add schedule content for all programs | DONE | Unified schedule implemented for all programs in schedule modal dialog | a8c9d7a
25 | Our Programs | Appearance | Age not prominently highlighted near image | Highlight age near image similar to hero banner style | DONE | Age badge enlarged with bigger padding (p-4), text-xl font, font-extrabold, uppercase tracking, and shadow-xl
WHAT WE OFFER SECTION
26 | What We Offer | Title | "Why Choose Us" needs renaming | Rename to "What We Offer" | DONE | Section renamed from "Why Choose Us" to "What We Offer" | 64e3e2f
27 | What We Offer | Appearance | Points displayed as static list | Display as auto-rotating photo cards that change automatically | DONE | Converted static image to auto-rotating carousel with 5 images cycling every 3.5s with fade transition
ADMISSION PROCESS SECTION
28 | Admission | Redundant | "Learn More About Curriculum" button | Remove | DONE | Entire Admission section removed from home page (component tag and import removed)
29 | Admission | Redundant | Admission Process steps section | Remove or simplify entire section | DONE | Entire Admission section removed from home page
30 | Admission | Redundant | Required Documents section | Remove | DONE | Entire Admission section removed from home page
31 | Admission | Redundant | Age Requirements section | Remove | DONE | Entire Admission section removed from home page
CURRICULUM SECTION
32 | Curriculum | Redundant | Entire Curriculum section (Key Learning Areas, Teaching Approach, Assessment, Global Perspective) | REMOVE entire Curriculum section | DONE | Curriculum section was already not rendered (no app-curriculum tag in home component)
CAREER / HIRING SECTION
33 | Career | Redundant | "Why Teach at DMA" benefits section | Remove (can include in coming years) | DONE | Entire Career/Hiring section removed from home page (component tag and import removed)
34 | Career | Function | Application link uses mailto:principal@davidandmaryacademy.in | Link to Canva application form or Teacher Application QR PDF | DONE | Entire Career/Hiring section removed from home page; Careers nav link also removed from header
IMAGES (ALL SECTIONS)
35 | All Sections | Images | Images need to be replaced with real student photos | Obtain photos from Justin and replace all placeholders | PENDING | Some real photos added in recent commits but more needed
EMAIL CORRECTION
36 | Sitewide | Email | Email shows principal@davidandmaryacademy.in | Change to davidmaryacademy@gmail.com everywhere; remove principal@ email | DONE | Email changed from principal@davidandmaryacademy.in to davidmaryacademy@gmail.com in footer and contact sections
TESTIMONIALS SECTION
37 | Testimonials | Content | Testimonials section from parents needed | Include parent testimonials with photos | DONE | "What Parents Say" section added with testimonials from VIDHYA and SANGAMI with 5-star ratings | a8c9d7a
FOOTER SECTION
38 | Footer | Content | Description paragraph beneath logo | Remove content beneath the logo | DONE | Description paragraph about exceptional early childhood education removed from beneath footer logo
39 | Footer | Function | Admission quicklink destination incorrect | Redirect to Apply for Admission link (JotForm) | DONE | Admission quicklink updated to JotForm URL with target=_blank, renamed to Apply for Admission
40 | Footer | Content | Operating hours incorrect | Change to: Mon-Friday 9am till 12:30 pm | DONE | Operating hours changed to Mon - Friday: 9:00 AM - 12:30 PM; Saturday hours removed
SUMMARY
Total Items | 40
Completed | 38
Pending | 2
Progress | 95%